## Sheet1
Criterion | FileName | Rating | SummaryAssessment
Strategic Relevance | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
1. Alignment to UNEP MTS, POW and strategic priorities | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Excellent alignment
2. Alignment to Donor/Partner strategic priorities | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Very good alignment
3. Relevance to global, regional, sub-regional and national environmental priorities | 1.10321_2024_ValTR_unep_gef_msp.pdf | S | Relevance varied but overall was Satisfactory
4. Complementarity with relevant existing interventions/coherence | 1.10321_2024_ValTR_unep_gef_msp.pdf | MS | HS complementarity, but it was underutilized. (Pending reassessment)
Quality of Project Design | 1.10321_2024_ValTR_unep_gef_msp.pdf | S | Design based on successful BEA projects, but TOC lacked some relevant market elements of ZCBs
Nature of External Context | 1.10321_2024_ValTR_unep_gef_msp.pdf | MU | Global pandemic of SARS- COVID-19 and earthquake in Türkiye were challenging
Effectiveness | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
1. Availability of outputs | 1.10321_2024_ValTR_unep_gef_msp.pdf | S | Outputs were high quality, available and well-utilized but should have been gathered together in one public access point by end of project
2. Achievement of project outcomes | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Targets for outcomes were exceeded
3. Likelihood of impact | 1.10321_2024_ValTR_unep_gef_msp.pdf | ML | Difficult to project, given lack of emissions data and long timeline(post-2030) for assumptions and drivers to hold for multiple countries
Financial Management | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
1. Adherence to UNEP’s financial policies and procedures | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | All policies and procedures followed
2. Completeness of project financial information | 1.10321_2024_ValTR_unep_gef_msp.pdf | MS | Nearly complete, except for final audit (underway) and PM’s explanation for one budget shortfall (IFC in-kind contribution)
3. Communication between finance and project management staff | 1.10321_2024_ValTR_unep_gef_msp.pdf | S | Regular, frequent and satisfactory; FMO and TM well- informed. See above for outstanding PM items
Efficiency | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Implemented fully within timeframe (with well-justified no- cost 7-month extension for MU nature of external context)
Monitoring and Reporting | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
1. Monitoring design and budgeting | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Designed with sufficient budget and indicators and owned by UNEP TMs and WRI PMs.
2. Monitoring of project implementation | 1.10321_2024_ValTR_unep_gef_msp.pdf | S | Plan fully developed and conducted in a timely manner by TMs and PMs. Some reporting revisions made for no-cost time extension.
3. Project reporting | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Reports match other evidence examined during TR; PM submitted detailed reports of stakeholder engagement and outreach (disaggregated by gender)
Sustainability | 1.10321_2024_ValTR_unep_gef_msp.pdf | ML
1. Socio-political sustainability | 1.10321_2024_ValTR_unep_gef_msp.pdf | ML | Near-term is likely, but longer term is highly dependent upon each country’s, state’s or city’s political commitments, continuity of governance and increased capabilities
2. Financial sustainability | 1.10321_2024_ValTR_unep_gef_msp.pdf | ML | Near-term, partially reliant upon international support. Long-term, the ZCB approach must demonstrate value to the financial sector in each locality and level of governance.
3. Institutional sustainability | 1.10321_2024_ValTR_unep_gef_msp.pdf | L | ZCB advocacy by UNEP, WRI and other partners likely will persist under their respective programs, possibly driven by the Buildings Breakthrough, GlobalABC and other UNEP and UNFCCC efforts.
Factors Affecting Performance | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
1. Preparation and readiness | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | All conditions met; first disbursement within 6 months.
2. Quality of project management and supervision | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Good communication maintained virtually by both parties, including smooth transitions during staff turnovers.
2.1 UNEP/Implementing Agency: | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
2.2 Partners/Executing Agency: | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS
3. Stakeholders’ participation and cooperation | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | High degree of participation, exceeding targets for number of participants and balanced gender participation
4. Responsiveness to human rights and gender equality | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | Consideration given to gender equality throughout project activities, outputs and outcomes. Human rights issues addressed in discussions of informal building sector
5. Environmental and social safeguards | 1.10321_2024_ValTR_unep_gef_msp.pdf | S | Safeguarding and risks well- considered and monitored; no negative environmental impacts
6. Country ownership and driven-ness | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | High degree of country and subnational ownership and driven-ness demonstrated, with many local-level ZCB policy & building efforts continuing post- project
7. Communication and public awareness | 1.10321_2024_ValTR_unep_gef_msp.pdf | MS | Good awareness at local stakeholder level; global audience communication could have been improved (lacks central access point for resources, post-project; this could negatively impact ease of ZCB project replication)
Overall Project Performance Rating | 1.10321_2024_ValTR_unep_gef_msp.pdf | HS | HS, especially considering diverse locations, short timeframe, medium-size project (& budget) and unanticipated external context (prolonged pandemic & a major earthquake)
Strategic Relevance | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | HS
1. Alignment to UNEP MTS, POW and Strategic Priorities | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | HS | The project was perfectly aligned with UNEP Medium Term Strategy 2018-2021. The project was also aligned with the different UNEP’s Programs of Work (PoW) during project implementation. Regarding the PoW 2022-2023, the project was aligned with the climate action sub-programme
2. Alignment to UNEP Donor/GEF/Partner strategic priorities | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | HS | The project was integrated in Sustainable Cities Integrated Approach Pilot (SCP-IAP) as a child project. The SC-IAP was funded by the GEF to promote the integration of environmental sustainability in planning and management initiatives for cities.
3. Relevance to global, regional, sub-regional and national environmental priorities | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | HS | The project was aligned with the SDG goal 11: Make cities and human settlements inclusive, safe, resilient, and sustainable The project was also aligned with UNDAF Brazil 2017-2021, with UNSDCF Brazil 2023-2027 and was fully aligned with the main guidelines of national environmental, urban and innovation policies, including the National Climate Change Policy, the City Statute, the National Environment Policy and the National Innovation Policy. The project was also aligned with the local level legal framework, namely with the Brasilia Sustainability Law and Recife Strategic Guidelines for the city.
4. Complementarity with existing interventions/ Coherence | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | The project was well integrated within the MCTI, the executing agency, and exhibited a strong capacity to coordinate with other ongoing projects and diverse stakeholders. It effectively participated in sustainable urban development events and successfully disseminated project results to relevant stakeholders at both central and local government levels, while also engaging civil society in these processes.
Quality of Project Design | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | During the project’s design, the main problems and challenges were identified. However, there's a gap in establishing clear causal relationships in the logic framework and anticipating risks. The Logic Framework could have provided a clearer illustration of these relationships, highlighting relevant causal pathways, assumptions and risks along with mitigation measures. It is important to acknowledge the fact that the project was developed by the implementation partners contributing to the ownership of the process. Project design includes specific activities and components to collect and share lessons learned and disseminate them and scale-up to other municipalities at national level.
Nature of External Context | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MU | The project was implemented against the backdrop of government transitions, shifting political agendas, changes in the priority of the environmental and climate agendas. This context created significant challenges for the project, especially at the national level, in promoting inter-ministerial cooperation to strengthen a national agenda for integrated urban planning, innovation, and sustainability. Additionally, the challenges of transitions made it difficult to establish mechanisms for knowledge exchange between managers at different levels of government. The project was also affected by the COVID-19 pandemic which had relevant impacts on project implementation strategies At the project management level, political and institutional changes in the governments in Brasilia and Recife and also in the MCTI introduced different procedures in the execution and monitoring of the project, requiring time to adapt and resume effective execution. unexpected challenge.
Effectiveness | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S
1. Availability of outputs | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | Most of the outputs were achieved, although some key outputs such as the IMS in Recife were not effectively delivered to the municipality. Given the context and some delays in implementation, the project proved a highly relevant capacity to deliver.
2. Achievement of project outcomes | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | The project had a satisfactory level of outcome achievement, enabling the mobilization of resources and expertise that usually are not available within local governments. The project was complex, involving multiple implementation partners and covering different cities with significant territorial dispersion. Moreover, high turnover among project implementation partners, including changes in the overall governance structure of MCTI, resulted in partners pursuing different agendas and made it difficult to establish a common understanding of the project goals. Delays in implementation did not allow to build these connections as most of the activities and outputs were finalized in the last year of project implementation.
3. Likelihood of impact | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | ML | The project had a relevant contribution to some of the intermediate states defined at the revised ToC. Some were fully reached such as greater collaboration between local technical institutions and departments and pilot investments improving the quality of live for local citizens and use of public spaces by women and children. Nonetheless, the project was overly segmented into four parts, with each partner implementing different agendas. Although the project promoted various coordination mechanisms, the segments lacked the necessary connection to consistently achieve intermediate states of impact. The most evident weakness in this connection was between the knowledge platforms and the interventions in Brasilia and Recife Achieving the scaling up of interventions in Brasilia and Recife to other Brazilian cities, during the project’s lifetime was always going to be challenging. Additionally, the institutional context and changes in political decision-makers at the federal level added complexity to an already complex situation
Financial Management | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S
1. Adherence to UNEP’s financial policies and procedures | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | The evaluation team was not made aware of any delays in the availability of funds that had any impact on project implementation. Project implementation partners had made budgetary adjustments during project lifetime, demonstrating a good adaptative management capacity. The financial management of CGEE led to some constraints at financial level.
2. Completeness of project financial information | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | Most of the required financial information was made available during the terminal evaluation. This included overall project budget, project expenditure sheets, reports on co-financing, audit reports, inventory of equipment and transfer of assets, project cooperation agreements. At the time of the terminal evaluation, only UNEP’s final financial execution sheets were not made available
3. Communication between finance and project management staff | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | Evidence suggests that the project manager has strong awareness of the current financial status of project , the financial staff had awareness of overall project progress and technical and financial staff worked together in resolving financial issues.
Efficiency | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MS | The project efficiency was hindered by: i) an implementation model that required high operational and coordination costs ii) permanent institutional changes at central and local government levels as also in implementing partners such as CGEE also contributed to some delays and inefficiencies in the project management; iii) The COVID pandemic also affected project implementation; iv) Coordination mechanisms were in place, but staff turnover and institutional changes hindered project efficiency. These changes affected the project's strategic direction and operational effectiveness; v) administrative burden adding to delays in implementation led to the partners to be focused on delivering their outputs and in this context, it was not simple to build a common understanding and a common path for project activities.
Monitoring and Reporting | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MS
1. Monitoring design and budgeting | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MU | Although the project regularly reported the status of each indicator in the Progress Implementation Reports, a robust monitoring plan shared by all implementation partners was lacking Given that the outcome indicators were not the most suitable, a revision of the project's results framework should have been undertaken. This would have allowed for a better understanding of the project's effects across its different components
2. Monitoring of project implementation | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MS | The project collected robust information on implementation, primarily focusing on outputs and deliverables. However, outcome monitoring was more complex and fragile due to weaknesses in the results framework and the absence of monitoring structures among the implementation partners. Additionally, the lack of baselines posed significant limitations. While Component 1 activities were mainly institutional, the pilot investments would have required baselines to effectively monitor the interventions' effects.
3. Project reporting | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | The project provides comprehensive and high-quality documentation of its implementation, with progress reports developed on time. Communication between UNEP, MCTI, and implementation partners was highly satisfactory despite the institutional changes and staff turnover that occasionally hindered project implementation.
Sustainability | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | ML
1. Socio-political sustainability | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | ML | The project made significant contributions in areas such as low carbon development, climate change adaptation and mitigation, sustainable urban development, and resilient cities. The incorporation of CITinova as a strategic program by the MCTI ensures that the guiding principles of the project will continue to be implemented by this relevant Ministry. However, it is important to acknowledge that political instability could shift the political context and deprioritize sustainable development and climate change agendas in future governments
2. Financial sustainability | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | L | Project components are strongly embedded in the implementing partners institutional framework and are being integrated in their financial commitments.
3. Institutional sustainability | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | L | In Brasilia and Recife, the project was fully implemented by government-level institutions (SEMA) or civil society organizations with institutional links to governmental bodies (ARIES). This approach ensured a good integration of the project's activities and results into the institutional governance of each project component.
Factors Affecting Performance | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S
1. Preparation and readiness | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MS | The project was approved in January 2017, the agreement with MCTI and implementing partners were signed in March 2018 and first disbursements to implementation partners were made in April / May 2018. A summary of the consultations during the project inception was provided and partners were engaged in the project design from the beginning and there was a relevant stakeholder engagement process
2. Quality of project management and supervision | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S
2.1 UNEP/Implementing Agency: | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | Overall supervision and project management were established at the MCTI with support and technical assistance from UNEP Brazil. the stability of UNEP Brazil's key staff was decisive in keeping the project on track
2.2 Partners/Executing Agency: | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | The implementing partners demonstrated strong capacity in executing project activities.
3. Stakeholders’ participation and cooperation | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S | Stakeholder engagement was a key pillar of the project throughout its implementation. Although some risks and problems were signed at the MTR, the project was able to promote a good engagement process in all its components, benefiting in some cases of the institutional changes
4. Responsiveness to human rights and gender equality | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | MS | The project did not develop a gender plan although the implementing partners have implemented some gender-related strategies. During the terminal evaluation a consistent gender approach or gender guidelines were not visible
5. Environmental and social safeguards | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | U | In the project document, an environmental and social safeguards checklist was presented but there was no consistent monitoring on safeguards besides the information provided in the project implementation reports under section 2.7.
6. Country ownership and driven-ness | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | HS | The project demonstrated highly satisfactory country ownership and drive
7. Communication and public awareness | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | HS | Communication activities and channels were well-targeted towards key audiences, fostering strong and comprehensive experience sharing between project partners and other interested groups and stakeholders
Overall Project Performance Rating | 3.9142_2024_te_unep_gef_spcmu_lac_Sustainable Cities in Brazil.pdf | S
(A) Strategic Relevance | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory
1. Alignment to UNEP MTS, POW and Strategic Priorities | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory | Strong performance as per PoW addressing objectives. Partners support the UNEP YEA strategy as innovative turn to networks increase coverage but needs more capacity building and coordination. (PAR 57 to 59)
2. Alignment to UNEP Donor/GEF/Partner strategic priorities | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory | The revised ToC proved relevant and appropriate. Constraints related to budget and the reduced number of UNEP staff. (PAR 60 to 62)
3. Relevance to global, regional, sub-regional and national environmental priorities | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory | Project demonstrated strong performance at the global level, with a cascade to regional and sub-regional levels that prioritise youth (PAR 63 to 66). Platforms implemented and disseminated (PAR 67 & 68). Considered a gap the government engagement (PAR 69 to 71)
4. Complementarity with existing interventions/ Coherence | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | Aligned with existing interventions of UN family, Association of Universities, Association of Commonwealth Universities, and numerous global sustainability networks in higher education and the private sector with the games industry (PAR 72 to 74)
(B) Quality of Project Design | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | It has a good design, logical strategy and the projects Tide Turners Plastic, Playing for the Planet Alliance, Green Collars job programmes, Little Book of Green Nudges and Sports for Nature were developed and implemented. Some constraints on advocacy of these projects where coordination was still being implemented, lesson learnt about sharing and the technical learning process were in an early stage. (PAR 74 to 82)
(C) Nature of External Context | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | The stakeholder map in three clusters reveals the diverse range of partners and presents the network as the key for success, highlighting the need for solid coordination abilities within the network but mainly within the UN sisters agencies and within the YEA team (PAR 83 to 88)
(D) Effectiveness | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory
1. Availability of outputs | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | Quantitative: all the outputs (2 for outcome 1 and 3 for outcome 2) surpass the target with good results for the output 1.1 and 1.2 and medium results for output 2.1 and 2.2, but with some gaps on output 2.3. The network partners undertook advocacy each way without sufficient inputs from the YEA project, indicating a non- driven communication strategy within all of them. Another challenge was the need to have a knowledge management (only happening where UNEP has regional offices) to force the curriculum changes needed. (PAR 89 to 104)
2. Achievement of project outputs and outcomes | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory | Solid alignment between the outcomes and the respective outputs, with a diversification of environmental education initiatives, and the integration of themes into universities and TVET curricula due to connections with network partners that empowered youth to lead the process and transform the implementation. However, there is a need for a unified corporate strategy for meaningful and strategically focused involvement regarding youth differences and specificities (PAR 105 to 109)
3. Likelihood of impact | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | The project's impact transcends mere numbers, and amplifies ‘marginalised voices’, referring to youth often being overlooked in global sustainability discussions e.g. green jobs initiative. The project would have benefited from higher engagement with youth groups, with a clear program developed for this end and coordination from UNEP. The training of youth on project management only happens in a few countries, and all sub-projects should be disseminated (PAR 110 to 113)
(E). Financial Management | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | None
1. Adherence to UNEP’s financial policies and procedures | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | There are several constraints to the budget; it is insufficient to perform all expected activities (PAR 114 & 115)
2. Completeness of project financial information | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Satisfactory | The available information is almost complete (PAR 116 & 117)
3. Communication between finance and project management staff | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderate Satisfactory | The team is small, making it easy to manage the communications related to finance (PAR 118)
(F). Efficiency | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | Results are economically appropriate way but bureaucracy is a challenge in all fields. Human resources staff have limited experience and a high turn-over (PAR 119 to 126)
(G). Monitoring and Reporting | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | None
1. Monitoring design and budgeting | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | One of the weakest areas without a budget. There is a template, but partners were not trained and cannot complete it. The responsibility is placed on partners about reasons for numbers differing with UNEP monitoring. There needs to be strong capacity building related to monitoring (PAR 127 to 129)
2. Monitoring of project implementation | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | Important to improve synergy between units and create time for reflection. Monitoring of the UN sister agency activities does not occur in the YEA. Need to move away from an urban centered approach and implement monitoring of peripheral areas (PAR 130 & 131)
3. Project reporting | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Satisfactory | The report needs to be more precise and answer all indicators with a synergy among the units of the YEA project. It will be benefic to incorporate the South-South cooperation and lesson learnt in the report. Network partners should follow the templates to facilitate reporting quality on results (PAR 132 to 134)
(H). Sustainability | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | None
1. Socio-political sustainability | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory | Project well connected with all UN, SUMMITS, COPs and World Forums, with the UN Assembly calling for environmental education. There are various challenges, the global scale leading to difficulties in direct engagements, requiring strong coordination with partners and an effective integration with all the UN sisters’ agencies involved to have a clear strategy (PAR 135 to 142)
2. Financial sustainability | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | Weak performance around financial sustainability and difficult long- term contracts with partner networks having the activities differently implemented (PAR 143 & 144)
3. Institutional sustainability | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderate Satisfactory | UNEP team readily available for connecting with partners and private sector, supported by the COP presence and availability of knowledge to present. Involvement of Government and the private sector is growing and in need of more advocacy (PAR 145 to 149)
(I). Factors Affecting Performance | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | None
1. Preparation and readiness | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | Preparation was satisfactory and project design of a good quality. The constants discussions within the team are very beneficial, providing possibilities for changes and new ideas if needed (PAR 150 & 151)
2. Quality of project management and supervision | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | None
2.1 UNEP/Implementing Agency: | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | UNEP was congratulated on its performance despite facing budget constraints, and communication has been improved (news, LinkedIn, website) (PAR 152 to 154)
2.2 Partners/Executing Agency: | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | Relationships with partners are good and based on technical respect, with coordination needing improvement to prevent working in silos (PAR 155 & 156)
3. Stakeholders’ participation and cooperation | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | YEA work is done through networks, making it important to have them in SUMMITS to discuss and highlight the achievement in several countries as the networks guide their sub-partners. Internally they also maintain technical meetings (PAR 157 to 159)
4. Responsiveness to human rights and gender equality | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | The Human Rights and gender equality occurs throughout the project (from project documents to implementation). The minorities are considered and respected, with leadership gender equality being incorporated (PAR 160 to 162)
5. Environmental and social safeguards | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Highly Satisfactory | The YEA project has demonstrated strong performance in its mandate of promoting the shift towards low-emissions education, improving the outcomes of environment education through youth participation and empowerment (PAR 163 & 164)
6. Country ownership and driven ness | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Unsatisfactory | Country ownership and driven-ness need to be improved. Efforts to support countries through network partners are ongoing to increase the understanding of youth leadership in this process. The Ministries responsible for environment in almost all countries do not have specific budgets (PAR 165 to 167)
7. Communication and public awareness | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Moderately Satisfactory | Core communications activities under the project related to knowledge management, communications and visibility are being developed and implemented with significant progress (PAR 168 & 169)
Overall Project Performance Rating | 4.2007_2024_te_unep_spes_global_Enironment education Youth.pdf | Satisfactory | None
Strategic Relevance | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | HS
1. Alignment to UNEP MTS, POW, and Strategic Priorities | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | HS | Relevant to several strategic priorities
2. Alignment to UNEP Donor/GEF/Partner strategic priorities | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | HS | Relevant to several strategic priorities
3. Relevance to global, regional, sub-regional and national environmental priorities | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | HS | Relevant to several strategic priorities
4. Complementarity with existing interventions/ Coherence | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | S | Complimentary with key existing interventions
Quality of Project Design | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Well documented design but highly ambitious
Nature of External Context | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MU | Challenges due to COVID-19, global and national economy, and national political situation
Effectiveness | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Delayed yet significant progress towards some planned outputs and outcomes. Project could have benefited from a no cost extension to finalize remaining tasks, especially RLF
1. Availability of outputs | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Delayed yet significant progress towards some planned outputs and outcomes. Project could have benefited from a no cost extension to finalize remaining tasks, especially RLF
2. Achievement of project outcomes | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Delayed yet significant progress towards some planned outputs and outcomes. Project could have benefited from a no cost extension to finalize remaining tasks, especially RLF
3. Likelihood of impact | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MU | Impact due to development of MEPS, but these have yet to be ratified. Also, RLF has yet to be established.
Financial Management | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Project ended despite having substantial remaining funding and progress on for establishing RLF.
1. Adherence to UNEP’s financial policies and procedures | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | NR | In accordance with UNEP-GEF guidelines
2. Completeness of project financial information | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | S | Financial documents made available with the evaluator were generally complete, updated, and clear.
3. Communication between finance and project management staff | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MU | Lack of clear communication has deprived project of a third no cost extension despite significant progress on RLF and leftover funds of USD 430,000
Efficiency | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Centralized management at Executing Agency. Procedural delays in project start. Human resource challenges, etc.
Monitoring and Reporting | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | S
1. Monitoring design and budgeting | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS
2. Monitoring of project implementation | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Frequent changes in project work plans at activity level made it difficult to track progress across years consistently
3. Project reporting | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | S | Detailed PIRs developed and approved
Sustainability | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | U
1. Socio-political sustainability | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | ML | The project’s goals are aligned with those of the Government and leading private sector lighting suppliers
2. Financial sustainability | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | U | Future financial support from donors will be required to continue building on project’s outcomes
3. Institutional sustainability | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MU | Lack of testing facilities in the country. Lack of implementation capacity.
Factors Affecting Performance | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS
1. Preparation and readiness | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
2. Quality of project management and supervision | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
2.1 UNEP/Implementing Agency: | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
2.2 Partners/Executing Agency: | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
3. Stakeholders’ participation and cooperation | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
4. Responsiveness to human rights and gender equality | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | NR | Please see above
5. Environmental and social safeguards | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | NR | Please see above
6. Country ownership and driven- ness | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
7. Communication and public awareness | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS | Please see above
Overall Project Performance Rating | 7.5799_2024_te_unep_spccm_msp_asia_pacific_ EE Lighting in Pakistan.pdf | MS
Strategic Relevance | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | Faith for Earth is highly aligned with global goals and UNEP strategy, demonstrating adaptation to ensure this over time.
• Alignment to UNEP MTS, POW and Strategic Priorities | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | High level of alignment which further strengthened with development of a new UNEP MTS during implementation. Links are explicit in the MTS and PoW.
• Alignment to donor/GEF/Partner Strategic Priorities | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | High level of response to global environmental needs and priorities and the strategic priorities of the wider UN system, donors and faith-based partners..
• Relevance to Regional, Sub-Regional and National Environmental PRiorities | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | Strong ability to adapt, incorporate new focus areas and respond to both challenges and opportunities based on priorities at national, regional and global levels..
• Complementarity with Existing Interventions | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | Complementarity and enhancement of existing efforts both within the UN and within FBOs was built into the fundamental design of Faith for Earth. It was particularly effective in complementing enabling existing environmental programmes within FBOs to understand, align with and participate in national, regional, and global environmental policy processes.
Quality of Project Design | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | Strong participatory design process ensured responsiveness to opportunity and existing potential partners, clearly articulated expected outputs and outcomes (with some revision over time), weaknesses in incorporating cross-cutting issues in original design.
Nature of External Context | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Favourable | COVID-19 impacted project delivery but the project also responded to new request and needs in the post-COVID recovery period. The project responded to the evolving global environmental agenda and UN policy processes, embracing these as a key opportunity for faith-based action.
Effectiveness | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | Faith for Earth achieved impressive reach, momentum and visibility, presenting a high likelihood of increased contribution of faith-based approaches to achievement of global environmental goals.
• Availability of outputs | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | Faith for Earth has demonstrated an impressive level of achievement against target indicators for all defined outputs. In most cases far exceeding stated targets.
• Achievement of project outcomes | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | Faith for Earth demonstrated an impressive level of achievement against target indicators for all defined putcomes. In most cases far exceeding stated targets.
• Likelihood of impact | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Likely | The significant outputs and outcomes point towards increased roles for and influence of faith-based actors.
Financial Management | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | Overall financial management was good, particularly considering the financial uncertainties and adaptation required during implementation.
• Adherence to UNEP’s financial policies | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | The project complied with UNEP policies and procedures for financial management. There were discrepencies and adjustments during implementation, reflecting a high level of financial uncertainty as well as fluid activity levels.
• Completeness of Financial Information | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | All records were available but greater narrative justification for changes would enhance this.
• Communication between finance and project management staff | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | No significant issues in communication were identified.
Efficiency | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | The project achieved a lot on a limited and unpredictable budget.
Monitoring and Reporting | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Satisfactory | The project had a clear monitoring plan which was deliverable with few additional resources, relying on project staff documentation on activities, together with wider reporting and knowledge outputs produced by the project. However, this monitoring plan could have been more effective at capturing unanticipated results or charting lessons around the process of change.
• Monitoring design and budgeting | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Satisfactory | The project had a clear monitoring plan, however it did not budget additional resources for monitoring and the plan did not maximise the capturing of achievements beyond those originally included in the results framework.
• Monitoring of project implementation | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Satisfactory | Project staff produced a high level of documentation on different activities relative to the resources they had, such as mission reports and annual reports. These captured different activities across the project but project monitoring reports needed to be cross-checked with other reporting to capture the full
• Project reporting | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Satisfactory | Reports were compiled against the results framework and showed impressive progress, however these did not fully explain the scope of all activities. It was hard to capture unanticipated outputs and outcomes in the regular project reporting.
Sustainability | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Satisfactory | The project has developed some building blocks for sustainability but these remain nascent and require further financial, technical and political support to achieve greater self-governance and sustainability.
• Socio-political sustainability | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Satisfactory | The increased recognition of faith-based actors within UNEP’s MTS and through other UN bodies points to an ongoing willingness to foster greater participation, influence and partnership that should sustain engagement and potential for influence.
• Financial sustainability | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Unsatisfactory | The project experienced regular periods of financial uncertainty but attracted additional funds through significant effort on the part of project staff. This financial uncertainty did limit potential to explore new avenues for impact in a strategic manner, making activity more opportunistic and short term.
• Institutional sustainability | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Moderately Satisfactory | Faith for Earth has paid a lot of attention to creating institutional channels for dialogue and representation, able to ensure a range of FBO’s from different beliefs are active and that they communicate back to a wider Faith for Earth Network. The creation of different structures within the wider network enables a degree of self-governance but they are not yet able to sustain their engagement at UN level independently.
Overall Project Performance Rating | 8.2053_2024_te_unep_speg_Faith for the Earth Initiative.pdf | Highly Satisfactory | A score of highly satisfactory is suggested due to strong strategic relevance and adaptation in support of UNEP’s wider environmental goals together with an exceptional level of achievement against targets (Effectiveness), despite less impressive ratings for enabling factors of efficiency and financial limitations.
Strategic Relevance | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS
1. Alignment to UNEP MTS, POW and strategic priorities | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS | In alignment with MTS 2014-2017, 2018- 2021, 2022-2025 and POW 2016-2017, 2018-2019, 2020-2021, 2022-2023.
2. Alignment to Donor/Partner strategic priorities | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS | In line with program 2 of strategic objective CW1 - Support enabling activities and promote their integration into national budgets and planning processes, national and sector policies and actions and global monitoring.
3. Relevance to global, regional, sub-regional and national environmental priorities | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS | Contributes to and facilitates fulfilling reporting obligations to the SC of the parties to the SC.
4. Complementarity with relevant existing interventions/coherence | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS | Builds upon other NIP and NIP-Update projects implemented by UNEP and other Agencies.
Quality of Project Design | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | The project fulfils all the formal requirements for a project document, with very few shortcomings, for example, the formulation of outputs and outcomes used in the project logical framework and TOC is not fully in alignment with the definition of outputs and outcomes at UNEP.
Nature of External Context | 9.9884_2024_ValTR_unep_gef_msp.pdf | MF | COVID-19 pandemic caused disruptions in project activities, especially at the national level in the 7 demonstration countries.
Effectiveness | 9.9884_2024_ValTR_unep_gef_msp.pdf | S
1. Availability of outputs | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | All 4 technical outputs are considered to be achieved – gap analysis report, development of toolkit and testing of toolkit, and the replication strategy.
2. Achievement of project outcomes | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | Direct outcome 1 regarding testing and usage of toolkit by the 7 demonstration countries –achieved; Direct outcome 2 with respect to the enhancement of knowledge via the integration of data from existing NIPs, NIP-Updates and NRs – partially achieved for the project, and work remains to be done by all the parties to the SC; Project outcome –achieved.
3. Likelihood of impact | 9.9884_2024_ValTR_unep_gef_msp.pdf | Likely | E-toolkit is developed and available online. It contains some quantitative data from the demonstration countries. Interest and commitment have been expressed, also from non-demonstration countries. The more countries use the toolkit and enter data, the more data will be available for analysis and further usage. Therefore, project is assessed to contribute to the envisaged impact, although this would also depend finally on the parties to the SC actually entering their POPs-related data into the toolkit.
Financial Management | 9.9884_2024_ValTR_unep_gef_msp.pdf | S
1. Adherence to UNEP’s financial policies and procedures | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | On the whole, the project has adhered to UNEP’s financial policies and procedures;2 payments have been made, albeit in compliance with the SSFAs, where the expenditure reports have been received only in May and June 2024.
2. Completeness of project financial information | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | All finance-related reports have been prepared and made available to the TR; 2 expenditure reports were prepared and submitted only in May and June 2024. Until then, the interim expenditure reports already submitted accounted for expenditure amounts considerably lower than the payment amounts already transferred.
3. Communication between finance and project management staff | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | Although regular coordination meetings or communication were not reported to have taken place, communication between finance and project management staff is reported to have been good and effective; all necessary information was provided by the PM to the FMO, who has then reviewed documentation and approved the payments; issues were not reported.
Efficiency | 9.9884_2024_ValTR_unep_gef_msp.pdf | MS | Project has experienced a delay of 2.5 years, one of the main reasons being the COVID-19 pandemic. A delay of 1 year has taken place after the commencement of the project; and lastly, in the finalization of the e-toolkit. The results of the TE of the previous NIP-Update projects 5525 and 5307, especially regarding Papua New Guinea, have not been considered during this project. UNEP ROs were not involved in project implementation. On the positive side, collaboration amongst partners is reported to have worked very well and existing resources within the UN system, for example, issuance of expert contracts via UNOPS, have been made use of, thus reducing administrative work for UNEP.
Monitoring and Reporting | 9.9884_2024_ValTR_unep_gef_msp.pdf | S
1. Monitoring design and budgeting | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | Project document entails M&E as an output. Although the term ‘monitoring’ is not explicitly mentioned, it was planned to be carried out via the Inception Workshop, the PSC meetings, the reports from project partners, half-yearly reports for UNEP-internal reporting and for the GEF and workplans.
2. Monitoring of project implementation | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | The Inception Workshop and 3 PSC meetings have taken place, as foreseen. However, despite the extension of the project, additional PSC meetings or other coordination meetings together with all project partners is not reported to have taken place.
3. Project reporting | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | Annual PIRs, a requirement of the GEF, have been prepared and submitted. The project partners have also prepared and submitted their progress reports. The project management staff has prepared quarterly progress reports. However, the non-participation of one country, initially foreseen to participate in the project, has not been documented consistently.
Sustainability | 9.9884_2024_ValTR_unep_gef_msp.pdf | HL
1. Socio-political sustainability | 9.9884_2024_ValTR_unep_gef_msp.pdf | HL | 186 countries are parties to the SC and are obliged to reporting under articles 7 and 15 of the SC. The project’s main output, the e-toolkit, facilitates the fulfilling of their reporting obligations. As such, risk to socio-political sustainability is considered to be low.
2. Institutional sustainability | 9.9884_2024_ValTR_unep_gef_msp.pdf | HL | The e-toolkit has been handed over to the BRS Secretariat, is under its institutional ownership, available online and can already be used to enter data.
3. Financial sustainability | 9.9884_2024_ValTR_unep_gef_msp.pdf | HL | The BRS Secretariat has confirmed that maintenance costs will be covered by its core budget.
Factors Affecting Performance | 9.9884_2024_ValTR_unep_gef_msp.pdf | S
1. Preparation and readiness | 9.9884_2024_ValTR_unep_gef_msp.pdf | MS | Although all project partners were aware of the project, there was a delay of over 1 year in the commencement of the activities; that is, over one year after the commencement of the project, the SSFAs with the countries were signed and the first IT expert recruited, in mid and late 2019.
2. Quality of project management and supervision | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | One change in PM has taken place; this is not reported to have any adverse effect on project implementation, as the current PM has worked as an expert on the project from mid-2018 to mid-2020. All the interviewed stakeholders have confirmed and appreciated the support and guidance provided by UNEP.
2.1 UNEP/Implementing Agency: | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | As elaborated above.
2.2 Partners/Executing Agency: | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | As elaborated above.
3. Stakeholders’ participation and cooperation | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | All the 7 demonstration countries and 3 BCSC/BCCC-SCRCs have actively engaged in the project activities. Due to different reasons, namely, COVID-19 and resource constraints, activities in Papua New Guinea could be completed only in mid-2024. Stakeholders are reported to have been very committed to the project and to chemicals’ management with regard to the SC.
4. Responsiveness to human rights and gender equality | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS | Theproject document has taken human rights and gender into account, and the outputs’ formulation entails gender aspects. A gender expert was recruited and workshops have been conducted by BCRC/BCCC-SCRCs including gender mainstreaming. A gender guidance was prepared with recommendations on how to incorporate gender in the NIPs and other projects.
5. Environmental and social safeguards | 9.9884_2024_ValTR_unep_gef_msp.pdf | HS | Project operates in the thematic area of environment. All formal criteria at UNEP for project approval, for example, ESERN, have been fulfilled. Project poses low risk to the environment and contributes to the envisaged positive impact on the environment.
6. Country ownership and driven-ness | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | All the 7 demonstration countries have actively participated in and carried out the activities foreseen in the project. Data collection, especially of new POPs, is reported to have been challenging in all the countries. Taking all the in- country limitations and constraints into consideration, ownership and driven- ness was satisfactory.
7. Communication and public awareness | 9.9884_2024_ValTR_unep_gef_msp.pdf | S | Public awareness was not foreseen in the project, with the exception of the website www.unep.org/topics/chemicals-and- pollution-action which can be freely accessed by all. The BCRC/BCCC- SCRCs have conducted workshops with the participation of other parties to the SC, which did not participate in the project, and communicated, amongst others, about the toolkit. The BRS Secretariat has communicated via e- mail to all the parties to the SC regarding the toolkit. However, coordination meetings or common communication of project results amongst key stakeholders has not taken place with the exception of the 3 PSC meetings.
Overall Project Performance Rating | 9.9884_2024_ValTR_unep_gef_msp.pdf | S
A. Strategic relevance | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | High relevant particularly with national and regional context and plans.
1. Alignment to UNEP’s MTS, POW and strategic priorities | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Very well aligned with UNEP MTS and PoW strategies.
2. Alignment to Donor/Partner strategic priorities | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Highly aligned with Objective 3 of the Biodiversity Focal Area, aiming to implement the Cartagena Protocol on Biosafety (CPB) under GEF 5 of the GEF-5 Strategy. It aligns with Outcomes 2.1, 2.2, and 2.3 of Objective 2.
3. Relevance to global, regional, sub-regional and national environmental priorities | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Well aligned with South -South Cooperation and SADC priorities and SDG 2 and Africa's Agenda 2063.
4. Complementarity with relevant existing interventions | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | The project aligned perfectly with the needs of countries in terms of both human health safety and Biosafety oriented towards transparent and regulated LMO management.
B. Quality of project design | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Overall, the quality of the project design was highly satisfactory.
C. Nature of external context | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | F | COVID-19 was the external event that had not been considered during the project's planning phase, and for which no one was prepared. Project management during COVID-19 was satisfactory, although it indeed posed challenges to consolidation and sustainability.
D. Effectiveness | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Highly Satisfactory effectiveness results.
1. Availability of outputs | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Outputs delivered despite unfavourable context created by COVID- 19.
2. Achievement of project outcomes | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Outcome achieved despite unfavourable context created by COVID-19.
3. Likelihood of impact | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | L | Potentially likely considering that is too early to analyse the project impact.
E. Financial management | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Highly Satisfactory project financial management.
1.Adherence to UNEP’s policies and procedures | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Very well aligned with UNEP procedures.
2.Completeness of project financial information | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Information completed and organized.
3.Communication between finance and project management staff | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Very frequent and transparent flow of information.
F. Efficiency | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | Cost-effectiveness well optimized
G. Monitoring and reporting | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | Positive and strong Monitoring and Reporting processes.
1. Monitoring design and budgeting | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | Well monitored and used.
2. Monitoring of project implementation | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | The project has been monitored adequately.
3.Project reporting | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | The project progress has been reported appropriately.
H. Sustainability | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | MU | Sustainability is the critical point of the project and has been mainly affected by COVID-19.
1. Socio-political sustainability | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | ML | Socio-political sustainability of the MCP-ICLT/ LMO project evaluated as moderately likely.
2. Financial sustainability | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | MUL | Financial sustainability is evaluated as moderately unlikely due to persistent financial challenges and gaps.
3. Institutional sustainability | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | ML | Despite the risks of staff turnover, ongoing training of permanent staff ensures positive institutional sustainability by maintaining a continuous transfer of knowledge and skills within the participating institutions of the MCP-ICLT/ LMO Project.
I. Factors affecting performance and cross- cutting Issues | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Satisfactory
1. Preparation and readiness | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | T h e p r o j e ct proactively addressed design weaknesses and adaptively responded to post-approval changes, especially in personnel management and financial realignment.
2. Quality of project management and supervision | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Very high quality of management of RAEIN-Africa and supervision of UNEP.
2.1 UNEP/Implementing Agency: | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | None | None
2.2 Partners/Executing Agency: | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | None | None
3. Stakeholders participation and cooperation | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | Highlights successful stakeholder integration and strong female involvement, despite logistical challenges, and emphasizes the critical support provided by Southern African technical advisors during the COVID-19 pandemic to maintain project momentum.
4. Responsiveness to human rights and gender equality | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | The project upheld human rights and promoted gender equity during the COVID-19 pandemic by supporting affected staff, involving educated women in key roles, and addressing personal challenges faced by team members, thereby maintaining ethical standards and advancing gender equality.
5. Environmental and social safeguards | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | The project met UNEP's environmental and social safeguards by regularly reviewing risk ratings and implementing eco-friendly practices to reduce resource usage and setting a standard for future initiatives.
6. Country ownership and driven- ness | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | HS | Strong country ownership and driven-ness by maintaining local engagement and control despite COVID-19 challenges, with local institutions actively advancing project goals and aligning outcomes with community needs and priorities.
7. Communication and public awareness | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | MS | Shortage in disseminating project results
Overall project rating | 12.5283_2024_te_unep_gef_sphpe_speg_Africa_LMO Testing.pdf | S | Satisfactory
None | 13.2049_2024_ValTR_unep.pdf | None | None
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | The project is relevant to strategies and work plan of UNEP, regional sea conventions, SDGs, and key donors’ policies.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | The project is well aligned with MTS 2017-21 and 22-25, POW 2020-21 and 22-23 and UNEA relevant resolutions.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Project is aligned with policies and visions of two major donors (Norway and Japan)
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | The project is coherent with the Regional Seas Strategic Directions 2017-2020 and SGD 6 and 14. As well as Regional Sea Conventions.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | The project complements with UNEP’s global campaigns and activities of GPML, GPNM and GWWI.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | The project document was comprehensive and followed UNEP’s project management guideline.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Unfavourable | Outbreak of COVID 19 was the significant external factor affected project negatively and positively.
Overall effectiveness rating adjusted from "Satisfactory" to “Moderately Satisfactory”. | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Most of outputs have been or will be achieved. Some Outcome have not been achieved. Link between overall outcome to intermediate state is weak.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Most of the outputs have been achieved
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | Project was strong in Outcome 1 and Outcome 3. The achievement of Output 2, of uptakes of good practices and introduction of innovative financial models was challenge.
Rating adjusted from "Likely" to “Moderately Likely” considering that some of the drivers (e.g., ‘scaled up or uptake of good practices’, ‘innovative financing and political and institutional supports’) are partially in place as indicated in paragraphs 192-193. | 13.2049_2024_ValTR_unep.pdf | Likely | Driver for overall outcome to intermediate state is not strong.
None | 13.2049_2024_ValTR_unep.pdf | None | None
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Good communication and adherence to UNEP’s financial policies were observed.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Adherence to financial policies and procedures were confirmed through interview.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | The reviewer confirmed that necessary financial documents were kept properly.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Communication and coordination between FMOs and PMOs were good.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | Project extended to replicate activities. Activities were realistic to the available budget.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | Implementation of monitoring can be improved by following monitoring plan
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | Project documents’ monitoring plan was in detail. Some indicators are not relevant.
Rating adjusted from "Satisfactory" to ‘Moderately Satisfactory’ The section on monitoring of project implementation only reports that “The project monitoring was chiefly conducted by reviewing reports from the executing organizations. There were some monitoring trips but not all the demonstration projects were visited, such as Wastewater project in Malaysia”. | 13.2049_2024_ValTR_unep.pdf | Satisfactory | The project monitoring was chiefly conducted by reviewing reports from the executing organizations.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | Regular reporting on PIMS and IPMS were confirmed.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Likely | Replications of activity in plastic, strong ownerships of country and existing partnership are positive factor of sustainability
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly likely | Countries were committed for the implementation of UNEA resolutions
Rating validated | 13.2049_2024_ValTR_unep.pdf | Likely | Additional funding for replication on plastic pollution is secured. Donor contribution and the number of donor have increased.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly likely | Complementarity with activities of GPLM, GPNM and GWWI, and other programs exist
None | 13.2049_2024_ValTR_unep.pdf | None | None
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Preparation, readiness and country ownerships are highly satisfactory.
Rating adjusted from "Satisfactory" to “Moderately Satisfactory”. The Review report states (e.g., para. 27, 90, 226 and 251) that a Project Steering Committee was not formed. | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Appropriate measures were taken for the preparation of project.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | There was no substantial challenge for project management. There was no functioning steering committee. High turnover of coordinators. Activities with GPML, GPNM and GWWI are well coordinated as well as working with executing partners.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | Active participations by the governments. Participations from private entities could have been improved.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Moderately Satisfactory | Issue of gender equity of the steering committee of GPNM was addressed. Publication on environmental justice and plastic pollution highlighted the human rights issues.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Environmental and social safeguards are considered as low risk.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Highly Satisfactory | Countries are driving intergovernmental processes and implementation of UNEA resolutions
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | Communication between the project and project partners were good.
Rating validated | 13.2049_2024_ValTR_unep.pdf | Satisfactory | The project was well planned and executed. It was highly relevant to UNEP’s strategy and SDGs. Outputs were achieved but linking to intermediate state could have been improved. The Project was implemented efficiently and already some activities were replicated. Coherence with global partnerships and strong country ownership makes the sustainability of project likely. Management of project had not major challenge except COVID19 but monitoring could have been improved.
A. Strategic Relevance | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1. Alignment to UNEP’s MTS, POW, and Strategic Priorities | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project is fully integrated in UN Environment’s Medium-Term Strategy (MTS) for 2018-2021 and supports the goals of the medium-term strategy under the Chemicals, Waste and Air Quality and Climate Change sub- p rogrammes.
2. Alignment to UNDA strategic priorities | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project is entirely aligned with the UNDA strategic priorities. It is focused on interagency coordination and working together on achieving the SDGs (UNDA 2023)
3. Relevance to regional, sub-regional and national (i.e. beneficiaries’) environmental priorities | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project is fully aligned with global, regional, and beneficiary’s environmental priorities, including Transport policies, Climate policies, and NMT strategies, in each country.
4. Complementarity with existing interventions/Coherence | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project is shows full complementarity, with no duplication, and has identified clear benefits to collaboration. UN partners (such as UNDP and UN- Habitat), in addition to country partners, are already supporting countries with TA, and full complementarity is a chieved.
B. Effectiveness | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1. Availability of outputs | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | S | The availability of outputs is satisfactory, achieved through a comprehensive dossier of documentation catalogued by UNEP. Although the quality of outputs are uneven across countries, all are of sufficient detail to logically and systematically progress toward the assigned outcome, and align with the associated project activity. Documentation of vulnerable group participation could be improved.
2. Achievement of outcomes | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | MS | Project outcomes are partially achieved, in all three project cities and countries. Although the project resulted in
None | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf |  | significantly improved engagement with vulnerable groups, and increased capacity among decision-makers, new policy was not yet developed. Commitments to develop new policy, however, in line with the project outcome goals, were made in each country.
3. Likelihood of impact (including an analysis of the project’s contribution to long-lasting results) | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | ML | Drivers to support transition from outputs to project outcome are in place. Assumptions for the change process partially hold – there is currently political will to move forward on plans for national and city commitments, although stakeholders note that this can be transient because of competing p riorities and political instability.
C. Financial Management | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1. Adherence to UNEP’s financial policies and procedures | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | S | There is no evidence of shortcomings in the project’s adherence to UNEP or donor policies.
2.Completeness of project financial information | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | S | Co-financing information Is available, and proof of commitments are delivered. Revisions or reallocations of the budget are evident and transparent. Awaiting proof of funds transfer. All project legal agreements are available. Summary report of project costs and budgets is available. No final audit is available yet.
3.Communication between finance and project management staff | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | There is evidence of a high level of communication between project team members and financial officers (in p erson communication and by email).
D. Efficiency | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1.Economic efficiency | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project was implemented in an efficient manner, within budget, despite Covid-19 related project delays, political instability, and staff turnover.
2.Timeliness | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | S | There was one no-cost extension.
3.Partnerships (engagement of implementing entity with national, regional and global level stakeholders; engagement with other implementing agencies) | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | S | The project benefited considerably from its good partnerships, and the partnerships of partners, but also experienced challenges where partnerships were less e ffective. Regional partnerships proved highly valuable.
E. Monitoring and Reporting | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1. Monitoring design and budgeting | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | MS | A project monitoring plan describing monitoring of outcomes and outputs based on indicators, its baseline, and target was coherent, consistent, and described clearly in the inception documentation. Monitoring reverted to a more default approach, however, due to Covid-19 disruptions. The monitoring was nevertheless in line with the sequential results framework and theory of change. The Results Framework, however, could have been better framed, with clear baseline statements with respect to the outcomes: both outcomes rely on indicators of ‘enhanced’ and ‘improved’. Regarding indicators, the Results Framework would have benefitted from normative statements to define certain outputs.
2. Monitoring of project implementation | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | S | Routine monitoring of project implementation at times missed important elements of outputs. The quality of data collection was uneven across countries.
3.Project reporting | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | All annual reports provided by UNEP to UNDA are complete and of high quality. Activities to support outputs and outcomes, as well as financial reporting and mitigation
None | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf |  | actions to resolve project challenges, are systematically d etailed.
F. Sustainability | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1. Socio-political sustainability | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | ML | Sustained project outcomes are highly dependent on political factors, in that decision-making and budget allocation ultimately rests with national governments.
2. Financial sustainability | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | ML | To implement the commitments developed for these outcomes requires substantial further financial input.
3. Institutional sustainability | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | ML
G. Cross Cutting Issues | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf
1. Sustainable Development Goals | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project aligns with and contributes to the achievement of all relevant SDGs.
2. Human Rights and Gender Equality (Also for UNDA) | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The principles of equality, inclusion and non-discrimination were central to the way in which the project was conceptualized, designed, and implemented.
3. Environmental, Social and Economic Safeguards | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | HS | The project by its very nature aimed at mitigating negative environmental, social, and economic impacts and did not have any direct negative impacts.
4. Communication and public awareness | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf | MU | There was no budget line for communication. Communication was rarely monitored for evidence of effect, reach, or otherwise for its engagement value, and there was a reliance on undifferentiated media targeting (social media in particular). Messaging was not always adapted or refined for different audiences. Stakeholders at review stage note that communication did not use interactive platforms, and communication by primarily one-way rather than a dialogue. Project activities were at times attributed under other p rojects also being undertaken by country partners.
Overall Project Rating | 16.2023I_2024_TR_unep_UNDA_Cycling Policies.pdf